## Agile Sprint Backlog
Story Point Estimation
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS
Story 1.1 – Image Capture | 3
1.1 — Setup image upload endpoint / camera input | 1 |  | Open
1.1 — Implement UI capture flow (web/mobile) | 1 |  | Open
1.1 — Basic image preprocessing (resize, normalize) | 1 |  | Open
Story 1.2 – Violation Detection | 8 |  | Open
1.2 — Integrate pretrained CV model / pipeline | 3 |  | Open
1.2 — Implement detection logic & rule matching | 2 |  | Open
1.2 — Threshold tuning and accuracy calibration | 2 |  | Open
1.2 — Unit tests / validation on sample images | 1 |  | Open
Story 1.3 – Standards Mapping | 5 |  | Open
1.3 — Build structured guideline DB (ADA/AODA refs) | 2 |  | Open
1.3 — Implement mapping engine (violation → guideline) | 1 |  | Open
1.3 — UI linking (show guideline reference in report) | 1 |  | Open
1.3 — Validate mapping with example cases | 1 |  | Open
Story 1.4 – Actionable Feedback | 5
1.4 — Recommendation rules engine (fix suggestions) | 2 |  | Open
1.4 — Create annotated visual overlays on images | 1 |  | Open
1.4 — Hook suggestions into report export | 1 |  | Open
1.4 — QA / verify recommendation accuracy | 1 |  | Open
Story 2.1 – Report Generation | 5
2.1 — Backend service to assemble report data | 2 |  | Open
2.1 — Design report template (HTML/PDF) | 1 |  | Open
2.1 — Implement export & storage (PDF/Download) | 1 |  | Open
2.1 — Report download UI & access control | 1 |  | Open
Story 2.2 – Dashboard Visualization | 8
2.2 — Backend aggregation APIs for metrics | 2 |  | Open
2.2 — Chart components (trend charts, counters) | 3 |  | Open
2.2 — Heatmap / visual overlay component | 2 |  | Open
2.2 — Integration, testing, and polish | 1 |  | Open
Story 3.1 – Data Labeling | 5
3.1 — Design labeling UI / workflow | 2 |  | Open
3.1 — Dataset schema & labeled data storage | 1 |  | Open
3.1 — Produce labeling guidelines / QA process | 1 |  | Open
3.1 — Seed labeling of examples (bootstrap) | 1 |  | Open
Story 3.2 – Model Retraining | 8
3.2 — Implement retraining pipeline (scripts, infra) | 3 |  | Open
3.2 — Training configuration & hyperparam experiments | 2 |  | Open
3.2 — Validation, metrics & model selection | 2 |  | Open
3.2 — Deploy new model + rollback plan | 1 |  | Open
Story 4.1 – Role-Based Access | 5
4.1 — Integrate auth (sign-in, session management) | 2 |  | Open
4.1 — Define RBAC roles & permission rules | 1 |  | Open
4.1 — Admin UI for user/role management | 1 |  | Open
4.1 — Access logging / audit hooks | 1 |  | Open
Story 5.1 – Scalability and Performance | 5
5.1 — Profile system & identify bottlenecks | 2 |  | Open
5.1 — Implement queueing / parallel processing / batching | 2 |  | Open
5.1 — Load testing and tune infra params | 1 |  | Open
Story 6.1 – Data Privacy and Security | 5
6.1 — Implement encryption (in-transit + at-rest) | 2 |  | Open
6.1 — PII detection & automated blurring/anonymization | 1 |  | Open
6.1 — Privacy settings / consent UI and logging | 1 |  | Open
6.1 — Prepare basic compliance documentation (PIPEDA/GDPR notes) | 1 |  | Open
Story 6.2 – Ethical AI Transparency | 3
6.2 — Implement confidence scores in outputs | 1 |  | Open
6.2 — Produce simple explainability snippets (saliency / short rationale) | 1 |  | Open
6.2 — Feedback/dispute submission flow | 1 |  | Open
Story 7.1 – Accessible Interface | 5
7.1 — Implement WCAG-required keyboard & ARIA support | 2 |  | Open
7.1 — Add high-contrast / text-scaling options | 1 |  | Open
7.1 — Screen-reader testing and fixes | 1 |  | Open
7.1 — Accessibility QA & remediation pass | 1 |  | Open
Story 7.2 – User Experience | 5
7.2 — UX flow refinement (upload → analysis → report) | 2 |  | Open
7.2 — Onboarding/tutorials and help tips | 1 |  | Open
7.2 — Write microcopy and error-state messaging | 1 |  | Open
7.2 — Usability testing and iterate fixes | 1 |  | Open
TOTAL | 75