## Tests
Test Case ID | Date Executed | Tester | Result (Pass/Fail) | Defect ID(s) (if any) | Notes
TC-1 | 2026-03-06 | Stepan | Pass |  | Automated test via audits.test.js passed. Token generated correctly.
TC-2 | 2026-03-06 | Stepan | Pass |  | Duplicate email properly rejected with 401.
TC-3 | 2026-03-06 | Anna | Pass |  | Valid credentials returned JWT and user profile correctly.
TC-4 | 2026-03-06 | Anna | Pass |  | Wrong password rejected; UI alert triggered as expected.
TC-5 | 2026-03-07 | Ryan | Pass |  | 403 Forbidden returned when no token provided in header.
TC-6 | 2026-03-07 | Ryan | Pass |  | Expired JWT correctly rejected by authorize middleware.
TC-7 | 2026-03-07 | Jen | Pass |  | Tested on physical Android device. Camera preview renders, frame counter increments.
TC-8 | 2026-03-08 | Stepan | Fail | BUG-01, BUG-02 | Upload triggered, but frame count was insufficient for 3D reconstruction, and the backend failed to handle the pipeline's response payload.
TC-9 | 2026-03-09 | Tiffany | Pass |  | Audit detail view successfully displays data from the completed pipeline job.
TC-10 | 2026-03-09 | Jen | Pass |  | History list successfully isolates audits per user.
TC-11 | 2026-03-09 | Tiffany | Pass |  | Profile screen displays correct email and role.
TC-12 | 2026-03-09 | Tiffany | Pass |  | Logout clears AsyncStorage. Redirected to Login.
TC-13 | 2026-03-09 | Anna | Pass |  | Empty multipart body rejected with 400 error. No DB record created.
TC-14 | 2026-03-09 | Jen | Pass |  | Pipeline successfully catches missing ArUco marker and updates job status to "failed" without crashing backend.
TC-08 | 2026-03-09 | Stepan | Pass | BUG-01, BUG-02 (Fixed) | RE-RUN: Adjusted frontend frame extraction rate. Fixed backend callback logic. Job now correctly queues and updates status.

## Bugs
Defect ID | Test Case(s) | Severity | Description | Status | Resolution Notes
BUG-01 | TC-08 | Medium | The frontend camera module was extracting frames at too low of a framerate. This resulted in too few images being sent to the Modal pipeline, causing the COLMAP 3D reconstruction to fail due to lack of overlap. | Closed | Modified the getThumbnailAsync extraction interval in the React Native app to capture frames more frequently, ensuring sufficient overlap for the pipeline.
BUG-02 | TC-08 | High | The server's POST /pipeline/callback route was incorrectly parsing the response payload sent by the Modal pipeline, causing the database to not update the audit status correctly. | Closed | Updated the backend callback function to correctly destructure scan_id and status from the incoming JSON body, allowing the database row to successfully transition from "queued" to "completed".